## Daily Tracker
Sl No | Month | Task Name | Sub task | Allocated Date | Target date of completion | Allocated To | Status (Completed/Pending) | Reason for Pending
1 | February | Literature Survey | Research paper collection and classification | 06-02-2026 | 07-02-2026 | Manasi Narkhede | Completed
2 | February | Literature Survey | Review papers on EDM and student performance prediction | 07-02-2026 | 08-02-2026 | Manasi Narkhede | Completed
3 | February | Literature Survey | Review papers on XGBoost for tabular data | 08-02-2026 | 09-02-2026 | Manasi Narkhede | Completed
4 | February | Literature Survey | Review papers on LSTM for behavioral sequences | 09-02-2026 | 10-02-2026 | Manasi Narkhede | Completed
5 | February | Literature Survey | Review papers on Transformers for text analysis | 10-02-2026 | 11-02-2026 | Manasi Narkhede | Completed
6 | February | Literature Survey | Review papers on multimodal fusion techniques | 11-02-2026 | 12-02-2026 | Manasi Narkhede | Completed
7 | February | Literature Survey | Review papers on SHAP and explainable AI | 11-02-2026 | 12-02-2026 | Manasi Narkhede | Completed
8 | February | System Design | Requirements analysis and scope definition | 13-02-2026 | 14-02-2026 | Manasi Narkhede | Completed
9 | February | System Design | Create High Level Design (HLD) document | 14-02-2026 | 15-02-2026 | Manasi Narkhede | Completed
10 | February | System Design | Create Low Level Design (LLD) document | 15-02-2026 | 16-02-2026 | Manasi Narkhede | Completed
11 | February | System Design | Prepare and submit project synopsis | 16-02-2026 | 17-02-2026 | Manasi Narkhede | Completed
12 | February | Environment Setup | Install Python 3.11 and core dependencies | 17-02-2026 | 18-02-2026 | Manasi Narkhede | Completed
13 | February | Environment Setup | Setup FastAPI, PyTorch, and ML libraries | 18-02-2026 | 19-02-2026 | Manasi Narkhede | Completed
14 | February | Environment Setup | Configure Docker and Docker Compose | 19-02-2026 | 20-02-2026 | Manasi Narkhede | Completed
15 | February | Data Collection | Collect tabular student data (GPA, attendance, demographics) | 20-02-2026 | 21-02-2026 | Manasi Narkhede | Completed
16 | February | Data Collection | Clean and validate tabular dataset | 21-02-2026 | 22-02-2026 | Manasi Narkhede | Completed
17 | February | Data Collection | Collect behavioral logs from LMS | 22-02-2026 | 23-02-2026 | Manasi Narkhede | Completed
18 | February | Data Collection | Collect textual data (essays, forum posts) | 23-02-2026 | 24-02-2026 | Manasi Narkhede | Completed
19 | February | Data Collection | Label and annotate all datasets | 24-02-2026 | 25-02-2026 | Manasi Narkhede | Completed
20 | February | Data Collection | Split data into train/validation/test sets | 25-02-2026 | 26-02-2026 | Manasi Narkhede | Completed
21 | March | Tabular Model | Feature engineering for tabular data | 27-02-2026 | 28-02-2026 | Manasi Narkhede | Completed
22 | March | Tabular Model | Handle missing values and outliers | 28-02-2026 | 01-03-2026 | Manasi Narkhede | Completed
23 | March | Tabular Model | Feature scaling and normalization | 01-03-2026 | 02-03-2026 | Manasi Narkhede | Completed
24 | March | Tabular Model | Train initial XGBoost classifier | 02-03-2026 | 03-03-2026 | Manasi Narkhede | Completed
25 | March | Tabular Model | XGBoost hyperparameter tuning with GridSearch | 03-03-2026 | 04-03-2026 | Manasi Narkhede | Completed
26 | March | Tabular Model | Evaluate XGBoost with cross-validation | 04-03-2026 | 05-03-2026 | Manasi Narkhede | Completed
27 | March | Tabular Model | Implement SHAP explainability for tabular model | 05-03-2026 | 06-03-2026 | Manasi Narkhede | Completed
28 | March | Behavioral Model | Preprocess behavioral sequences (padding, truncation) | 06-03-2026 | 07-03-2026 | Manasi Narkhede | Completed
29 | March | Behavioral Model | Temporal normalization and feature extraction | 07-03-2026 | 08-03-2026 | Manasi Narkhede | Completed
30 | March | Behavioral Model | Design LSTM architecture (layers, units, dropout) | 08-03-2026 | 09-03-2026 | Manasi Narkhede | Completed
31 | March | Behavioral Model | Implement LSTM model in PyTorch | 09-03-2026 | 10-03-2026 | Manasi Narkhede | Completed
32 | March | Behavioral Model | Train LSTM on behavioral data | 10-03-2026 | 11-03-2026 | Manasi Narkhede | Completed
33 | March | Behavioral Model | Evaluate LSTM with AUC and confusion matrix | 11-03-2026 | 12-03-2026 | Manasi Narkhede | Completed
34 | March | Text Model | Text preprocessing (lowercasing, punctuation removal) | 12-03-2026 | 13-03-2026 | Manasi Narkhede | Completed
35 | March | Text Model | Tokenization with DistilBERT tokenizer | 13-03-2026 | 14-03-2026 | Manasi Narkhede | Completed
36 | March | Text Model | Generate embeddings with DistilBERT | 14-03-2026 | 15-03-2026 | Manasi Narkhede | Completed
37 | March | Text Model | Fine-tune DistilBERT for classification | 15-03-2026 | 16-03-2026 | Manasi Narkhede | Completed
38 | March | Text Model | Evaluate text model with F1-score and precision | 16-03-2026 | 17-03-2026 | Manasi Narkhede | Completed
39 | March | Fusion | Design late fusion ensemble architecture | 17-03-2026 | 18-03-2026 | Manasi Narkhede | Completed
40 | March | Fusion | Implement weighted meta-learner | 18-03-2026 | 19-03-2026 | Manasi Narkhede | Completed
41 | March | Fusion | Train fusion ensemble on all modalities | 19-03-2026 | 20-03-2026 | Manasi Narkhede | Completed
42 | March | Fusion | Calibrate probabilities with Platt scaling | 20-03-2026 | 21-03-2026 | Manasi Narkhede | Completed
43 | March | Fusion | Evaluate fusion model end-to-end | 21-03-2026 | 22-03-2026 | Manasi Narkhede | Completed
44 | March | Explainability | Integrate SHAP for fusion model | 22-03-2026 | 23-03-2026 | Manasi Narkhede | Completed
45 | March | Explainability | Implement NLG summarizer for explanations | 23-03-2026 | 24-03-2026 | Manasi Narkhede | Completed
46 | March | Explainability | Test explainability with sample predictions | 24-03-2026 | 25-03-2026 | Manasi Narkhede | Completed
47 | March | Backend | Setup FastAPI project structure | 25-03-2026 | 26-03-2026 | Manasi Narkhede | Completed
48 | March | Backend | Implement database models with SQLAlchemy | 26-03-2026 | 27-03-2026 | Manasi Narkhede | Completed
49 | March | Backend | Create Alembic migrations | 27-03-2026 | 28-03-2026 | Manasi Narkhede | Completed
50 | March | Backend | Implement JWT authentication | 28-03-2026 | 29-03-2026 | Manasi Narkhede | Completed
51 | March | Backend | Implement /auth/register and /auth/login endpoints | 29-03-2026 | 30-03-2026 | Manasi Narkhede | Completed
52 | March | Backend | Implement /predict endpoint with model inference | 30-03-2026 | 31-03-2026 | Manasi Narkhede | Completed
53 | March | Backend | Implement /cohort/{id} endpoint | 31-03-2026 | 01-04-2026 | Manasi Narkhede | Completed
54 | March | Backend | Add rate limiting with SlowAPI | 01-04-2026 | 02-04-2026 | Manasi Narkhede | Completed
55 | March | Backend | Add input validation with Pydantic | 01-04-2026 | 02-04-2026 | Manasi Narkhede | Completed
56 | April | Frontend | Setup React 19 + Vite + Tailwind CSS | 03-04-2026 | 04-04-2026 | Manasi Narkhede | Completed
57 | April | Frontend | Configure React Router and Zustand store | 04-04-2026 | 05-04-2026 | Manasi Narkhede | Completed
58 | April | Frontend | Build login page with form validation | 05-04-2026 | 06-04-2026 | Manasi Narkhede | Completed
59 | April | Frontend | Build cohort dashboard layout | 06-04-2026 | 07-04-2026 | Manasi Narkhede | Completed
60 | April | Frontend | Add risk distribution charts with Recharts | 07-04-2026 | 08-04-2026 | Manasi Narkhede | Completed
61 | April | Frontend | Build student risk table component | 08-04-2026 | 09-04-2026 | Manasi Narkhede | Completed
62 | April | Frontend | Add sorting and filtering to risk table | 09-04-2026 | 10-04-2026 | Manasi Narkhede | Completed
63 | April | Frontend | Build explanation modal component | 10-04-2026 | 11-04-2026 | Manasi Narkhede | Completed
64 | April | Frontend | Add SHAP visualization to explanation modal | 11-04-2026 | 12-04-2026 | Manasi Narkhede | Completed
65 | April | Frontend | Add NL summary to explanation modal | 12-04-2026 | 13-04-2026 | Manasi Narkhede | Completed
66 | April | Integration | Connect frontend to backend API | 13-04-2026 | 14-04-2026 | Manasi Narkhede | Completed
67 | April | Integration | Test end-to-end prediction flow | 14-04-2026 | 15-04-2026 | Manasi Narkhede | Completed
68 | April | Integration | Fix CORS and authentication issues | 14-04-2026 | 15-04-2026 | Manasi Narkhede | Completed
69 | April | Testing | Write backend unit tests with pytest | 15-04-2026 | 16-04-2026 | Manasi Narkhede | Completed
70 | April | Testing | Write backend integration tests | 16-04-2026 | 17-04-2026 | Manasi Narkhede | Completed
71 | April | Testing | Write frontend component tests with Vitest | 17-04-2026 | 18-04-2026 | Manasi Narkhede | Completed
72 | April | Testing | Run full test suite and fix failures | 18-04-2026 | 19-04-2026 | Manasi Narkhede | Completed
73 | April | Docker | Create Dockerfile for backend | 19-04-2026 | 20-04-2026 | Manasi Narkhede | Completed
74 | April | Docker | Create Dockerfile for frontend | 19-04-2026 | 20-04-2026 | Manasi Narkhede | Completed
75 | April | Docker | Create docker-compose configuration | 20-04-2026 | 21-04-2026 | Manasi Narkhede | Completed
76 | April | Deployment | Setup AWS EC2 instance | 21-04-2026 | 22-04-2026 | Manasi Narkhede | Completed
77 | April | Deployment | Configure Nginx reverse proxy and SSL | 22-04-2026 | 23-04-2026 | Manasi Narkhede | Completed
78 | April | Documentation | Write Final Internship Report | 23-04-2026 | 27-04-2026 | Manasi Narkhede | Completed
79 | April | Documentation | Create presentation slides | 27-04-2026 | 28-04-2026 | Manasi Narkhede | Completed
80 | April | Documentation | Record demo video and submit | 28-04-2026 | 30-04-2026 | Manasi Narkhede | Completed