## Weekly Tracker
Project name | Multimodal Academic Performance Prediction System
Mentor name | Mr. Rithik Raj Vaishya
Student | Manasi Narkhede (DS24M11)
Description | An end-to-end system for predicting student academic risk from three data sources: tabular student records, behavioral LMS activity, and free-text submissions.
Slno | Task | Assigned to | Start date | End date | Status | Remarks
Week 1 | Research paper gathering and literature survey on student performance prediction using ML | Manasi Narkhede | 06-02-2026 | 12-02-2026 | Completed | Reviewed 30+ papers on EDM, multimodal learning analytics, XGBoost, LSTM, Transformers
2 | Study existing systems and identify gaps in current approaches | Manasi Narkhede | 08-02-2026 | 12-02-2026 | Completed | Identified need for multimodal fusion with explainability
3 | Document findings and prepare initial literature review chapter | Manasi Narkhede | 10-02-2026 | 12-02-2026 | Completed | Literature review chapter drafted
Week 2 | Define system requirements and create High Level Design (HLD) document | Manasi Narkhede | 13-02-2026 | 15-02-2026 | Completed | Architecture diagram and component design completed
5 | Create Low Level Design (LLD) document with module specifications | Manasi Narkhede | 14-02-2026 | 17-02-2026 | Completed | API contracts, database schema, and class diagrams ready
6 | Prepare project synopsis and get approval from mentor | Manasi Narkhede | 15-02-2026 | 19-02-2026 | Completed | Synopsis submitted and approved
Week 3 | Set up development environment: Python 3.11, FastAPI, PyTorch, Docker | Manasi Narkhede | 20-02-2026 | 22-02-2026 | Completed | All dependencies installed and environment tested
8 | Configure PostgreSQL database and create schema for students, predictions, cohorts | Manasi Narkhede | 21-02-2026 | 23-02-2026 | Completed | Database schema with Alembic migrations ready
9 | Collect and clean tabular student data (GPA, attendance, demographics) | Manasi Narkhede | 22-02-2026 | 26-02-2026 | Completed | Dataset with 1000+ student records prepared
Week 4 | Implement tabular data preprocessing pipeline (scaling, missing values, feature engineering) | Manasi Narkhede | 27-02-2026 | 01-03-2026 | Completed | Pipeline handles categorical encoding and normalization
11 | Train and evaluate XGBoost model for tabular features | Manasi Narkhede | 28-02-2026 | 03-03-2026 | Completed | Achieved 85.2% accuracy on test set
12 | Implement SHAP explainability for tabular predictions | Manasi Narkhede | 02-03-2026 | 05-03-2026 | Completed | SHAP summary plots and force diagrams integrated
Week 5 | Collect behavioral data from LMS (clickstreams, login patterns, time-on-task) | Manasi Narkhede | 06-03-2026 | 08-03-2026 | Completed | Behavioral logs with temporal sequences extracted
14 | Preprocess behavioral sequences (padding, truncation, temporal normalization) | Manasi Narkhede | 07-03-2026 | 10-03-2026 | Completed | Sequences normalized to 50 timesteps
15 | Train and evaluate LSTM model for behavioral data | Manasi Narkhede | 08-03-2026 | 12-03-2026 | Completed | LSTM achieves 82.7% accuracy with AUC 0.89
Week 6 | Collect textual data (essays, forum posts, assignment submissions) | Manasi Narkhede | 13-03-2026 | 15-03-2026 | Completed | 500+ text samples collected and labeled
17 | Implement text preprocessing (tokenization, DistilBERT embeddings) | Manasi Narkhede | 14-03-2026 | 17-03-2026 | Completed | BERT tokenizer and embedding pipeline ready
18 | Fine-tune Transformer model for educational text classification | Manasi Narkhede | 15-03-2026 | 19-03-2026 | Completed | DistilBERT achieves 87.1% F1-score
Week 7 | Implement late fusion ensemble with weighted meta-learner | Manasi Narkhede | 20-03-2026 | 22-03-2026 | Completed | Fusion combines XGBoost, LSTM, and Transformer outputs
20 | Calibrate fusion ensemble probabilities and evaluate | Manasi Narkhede | 21-03-2026 | 24-03-2026 | Completed | Calibration with Platt scaling completed
21 | Integrate NLG summarizer for natural language explanations | Manasi Narkhede | 23-03-2026 | 26-03-2026 | Completed | Explanations generated for each prediction
Week 8 | Develop FastAPI backend structure with routers and middleware | Manasi Narkhede | 27-03-2026 | 29-03-2026 | Completed | Modular API structure with error handling
23 | Implement JWT authentication and role-based access control | Manasi Narkhede | 28-03-2026 | 31-03-2026 | Completed | Secure token-based auth with bcrypt hashing
24 | Build prediction endpoints with input validation and caching | Manasi Narkhede | 29-03-2026 | 02-04-2026 | Completed | Endpoints tested with 100+ requests
Week 9 | Setup React 19 + Vite + Tailwind CSS development environment | Manasi Narkhede | 03-04-2026 | 04-04-2026 | Completed | Frontend environment with hot reload configured
26 | Build login page with JWT token management | Manasi Narkhede | 04-04-2026 | 06-04-2026 | Completed | Secure login with form validation
27 | Build cohort dashboard with risk distribution charts | Manasi Narkhede | 05-04-2026 | 08-04-2026 | Completed | Interactive dashboard with Recharts visualizations
Week 10 | Build student risk table with sorting and filtering | Manasi Narkhede | 09-04-2026 | 11-04-2026 | Completed | Sortable table with search functionality
29 | Build explanation modal with SHAP charts and NL summaries | Manasi Narkhede | 10-04-2026 | 13-04-2026 | Completed | Modal shows SHAP force plot and text explanation
30 | Connect frontend to backend API and test end-to-end flow | Manasi Narkhede | 11-04-2026 | 15-04-2026 | Completed | Full integration tested with real data
Week 11 | Write backend unit tests with pytest (17 test files) | Manasi Narkhede | 16-04-2026 | 18-04-2026 | Completed | 95% code coverage on API endpoints
32 | Write frontend tests with Vitest and React Testing Library | Manasi Narkhede | 17-04-2026 | 19-04-2026 | Completed | Component and integration tests passing
33 | Dockerize application with multi-stage builds | Manasi Narkhede | 18-04-2026 | 20-04-2026 | Completed | Docker Compose with nginx, backend, frontend, db
Week 12 | Deploy on AWS EC2 with SSL certificates and domain | Manasi Narkhede | 21-04-2026 | 24-04-2026 | Completed | Live deployment with HTTPS and CloudWatch
35 | Prepare Final Internship Report with all chapters and references | Manasi Narkhede | 23-04-2026 | 28-04-2026 | Completed | Complete report with TOC, tables, and 30+ references
36 | Prepare presentation and demo video | Manasi Narkhede | 26-04-2026 | 30-04-2026 | Completed | PPT and demo video ready for submission